## CAT Metrics
CAT Delivery Excellence Tracker | [22 empty] | Total Teams to Parse: | 26 | Sprint Number: | July 2nd Sprint | Sprint Start Date: | 15th July 2026 | Sprint End Date: | 30th july 2026
|  | Delivery |  |  |  |  | Client Health |  |  |  |  | Capability and gaps |  | Project Automation Metrics
Engagement | SPOC | Story Points Assigned | Story Points Completed | No of User Stories/Tasks Assigned | No of User Stories/Tasks Completed | No of User Stories/Tasks pushed to next Sprint | Defect Leakage (%) G ≤5 · R >10 | Production Incidents (#) G ≤0 · R >2 | No of Open Risks & Issues (#) G ≤2 · R >4 | No of SOW Milestones | Escalations (#) G ≤0 · R >2 | No of Automation Tool proficiencies | No of Build Tool proficiencies | Automation Coverage (%) G ≥75 · R <55 | Automation Stability (%) G ≥95 · R <85 | Regression Run Time (hrs) Track trend | Regression execution Time (hrs) Without Automation | No of Automation Bugs Reported | Knowledge Transfer (#) G ≥2 · R <1 | Reusable Assets (#) G ≥2 · R <1 | Effort Savings (hrs) Track trend | Savings (INR)
CAT - Advanced Calculator | Dinesh D | 24 | 24 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 40 | 90 | 1.5 | 4 | 0 | NA | NA | NA | NA
CAT Parts pricing | Ansar, Rafia | 32 | 32 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | 0 | NA | NA | NA | NA
CAT- Technician Toolbox (TTB) | R, Nazreenfathima | 48 | 43 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 40 | 94 |  | 15 days | 1 | 2 | 0
CAT-MCUI-Extension | Rajesh, Kamble | 3 | 3 | 1 | 1 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
CAT-MineStar Modularization | Shweta Kumari | 30 | 30 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 50 | Na | NA | NA | 1 | NA | NA | NA | NA
Common Services Program - Extension | Panuganti, Sai Teja | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | NA | NA | NA | NA | 0 | NA | NA | NA | NA
Dealer Service Portal | Salman Y, Mohammed | 40 | 25 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 85 | 90 | 0.5 | 8 | 4 | NA | NA | NA | NA
DSP – BAAS/VLP/Customer Admin Tool | Ilangovan, Prahadhees
Dealer Service Portal - Billing | Pradeep Kumar S | 32 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 40 | 90 | 0.5 | 8 | 2 | NA | NA | NA | NA
Dealer Service Portal - CIS | Danish, Mohammed/Vijay S | 15.5 | 10 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 80 | 80 | 1.5 | 24 | 4 | NA | NA | NA | NA
Dealer Service Portal - Gambit | Lahiri, Priyobroto | 16 | 16 | 4 | 2 | 0 | 0 | 0 | 1 | 2 | 0 | 2 | 2 | 100 | 96 | 0.1 | 16 | 3 | NA | NA | NA | NA
Foresight | S, Vijay | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Leadership Table 2 | Priyanka Balladkar | 15 | 5 | 3 | 1 | 0 | NA
PCC - eCommerce - UI | Soman, Chetan | 8 | 8 |  |  |  | 0 | 0
PSCS-Backend | Modalavalasa, Suryaprabha | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 60 | >90 | 2 | 2 | 3 | NA | NA | NA | NA
PSCS-Performance | M, Himabindu | 10 | 10 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 90 | 90 | 7 | 2 | 0 | NA | NA | NA | NA
VLP - Invaders | I, Raghul | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 16 | 0 | NA | NA | NA | NA
VLP - Jetson | Rubalaxmi A | 28.25 | 28.25 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | NA | 79 | 90 | 7 | 30 | 0 | NA | NA | NA | NA
VLP - Skyliner | Harish Kumar | 30 | 30 | 17 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 85 | 90 | NA | NA | NA | NA | NA | NA | NA
VLP - Sprinters | Rahul More | 8 | 8 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 85 | 88.5 | 5 | 24 | 2 | NA | NA
Warranty | Jerom Maria Selvam | 17.5 | 17.5 | 18 | 18
CAT- Horizon App | Suhail A Mohammed | 8 | 8 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 85 | 95 | 3.5 | 16 | 5 | NA | 0 | NA | NA
Remote Asset Monitoring - VisionLink | Dilleswara Rao, Lakhinana | 8 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | <70 | 1.5 | 30 | 0 | NA | NA | NA | NA
CAT - SIS2Go | Ramesh, Renugadevi | 24 | 24 | 4 | 4 | 0 | 0 | 0 | 0 | NA | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
CAT -MyUsed | Santhosh D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
DSP Galaxy | Sangeetha | 24 | 18 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 100 | 80 | NA | NA | 0 | NA | NA | NA | NA

## CAT Details
CAT Delivery Excellence Tracker - Details | [20 empty] | Total Teams to Parse: | 19
|  | Delivery | Client Health |  |  |  |  | Capability Gaps |  |  |  |  | Project Automation Metrics |  |  | Compliance |  | Project Info
Engagement | SPOC | User Stories/Tasks Assigned (Short Point(s)) | Defect Leakages (Short Point(s)) | Production Incidents (Short Point(s)) | Open Risks & Issues (Short Point(s)) | SOW Milestones (Short Point(s)) | Escalations RCA (Escalation Reason) | Automation Tool proficiencies Required (Tool Name(s)) | Build Tool proficiencies Required (Tool Name(s)) | Inline with Cloud & DevOps Platform Proficiencies (Azure DevOps, AWS) (Yes/No) | CI-CD Pipeline Setup Proficiency (Yes/No) | Knowledge transfer documentation Prepared (Yes/No) | Automation Bugs Reported (Short Point(s)) | CI/CD Maturity (Yes/No) | Assets Reused (Short Point(s)) | Deloitte Timesheet Filled (Yes/No) | Tenrox Timesheet Filled (Yes/No) | CAT Manager | Engagement Code | LOB Lead
CAT - Advanced Calculator | Dinesh D | Production Bugs¦Automation Task ¦Security Testing ¦ | 0 | 0 | 0 | 0 | 0 | Selenium ¦ Karate framework | Maven | Yes | Yes | No | 0 | Yes | 0 | Yes | Yes | Krishna Srinivasan
CAT Parts pricing | Ansar, Rafia | 6 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | No | 0 | NA | 0 | Yes | NA
CAT- Technician Toolbox (TTB) | R, Nazreenfathima | 5 | 0 | 0 | 0 | 0 | 0 | Python ¦ Robot Framework |  | Yes | Yes | Yes | 0 | Yes | 0 | Yes | NA | Sridhar Athota | CAT02557-01-02-01-1000 | Nazreen
CAT-MCUI | Rajesh, Kamble | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
CAT-MineStar Modularization | Shweta Kumari | 6 | NA | NA | NA | NA | NA | Playwright | NA | Yes | Yes | NO | 1 | NA | NA | Yes | NA
Common Services Program - Extension | Panuganti, Sai Teja | KT Sessions ¦ POC on new framework | NA | NA | NA | NA | NA | Python,Behave | NA | Yes | Yes | No | NA | NA | NA | Yes | Yes | Mugesh Ganesh | CAT02610-01-02-01-1000 | Shwetha Kumari
Dealer Service Portal | Salman Y, Mohammed | Regression Fix ¦ Release Feature Validation ¦ Release Feature Regression Automation | NA | NA | NA | NA | NA | Playwright | Maven | Yes | Yes | No |  |  |  | Yes | Yes | Annamalai | CAT02510-01-02-01-1000 | Rajgovind
DSP – BAAS/VLP/Customer Admin Tool | Ilangovan, Prahadhees
Dealer Service Portal - Billing | Pradeep Kumar S | New Features ¦ Automation Tasks ¦ UI ¦ API | NA | NA | NA | Revenue items API Automation¦ Charges API Automation¦ UI Automation ¦ | NA | Karate¦ Playwright | Maven¦ npm | Yes | Yes- API No- UI | Yes | UI bugs | No | NA | Yes | Yes | Indumathi​ |  | Rajgovind
Dealer Service Portal - CIS | Danish, Mohammed/Vijay S | Regression Fix ¦ Release Feature Validation ¦ Release Feature Regression Automation | NA | NA | NA | NA | NA | Playwright ¦ Typescript | NPM | Yes | Yes | Yes | 4 | Yes | NA | Yes | Yes | Renugadevi | CAT02517-01-01-01-1000 | Rajgovind
Dealer Service Portal - Gambit | Lahiri, Priyobroto | Update Billrun Testcases ¦ Validate Notification Services ¦ Validate Billrun Entitlements ¦ Testcase Creation for Charges enhancement | NA | NA | Client doesn’t create RTM document, directly moves to Test case creation from ADO Feature | Billrun Service Moved to prod ¦ Charges Enhancement deployment on 31st July | NA | Karate ¦ Playwright | Maven ¦ NPM | Yes | Yes | Yes | Charge is created with 200ok response when servicestartDate > ServiceEndDate ¦ Billrun workflow stuck at Posted status in Post Billrun Workflow | Yes | NA | Yes | Yes | Arun Srinivasan | CATX0552-01-01-01-1000 | Rajgovind
Foresight | S, Vijay | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Leadership Table 2 | Priyanka Balladkar
PCC - eCommerce - UI | Soman, Chetan
PSCS-Backend | Modalavalasa, Suryaprabha | User stories for Blocks migration and new PSCS enhancements | 0 | 0 | 0 | 0 | 0 | Playwright with Python | No | YES | YES | NA | 0 | NA | NA | YES | NA | Vineela Kotra | CAT02510-01-02-01-1000 | Raj Govind
PSCS-Performance | M, Himabindu
VLP - Invaders | I, Raghul | Regression Testing ¦ API validation on impacted area ¦ Production issue Retesting | 0 | 0 | 0 | 0 | 0 | Selenium, Hybrid Framework | No | Yes | Yes | No | 0 | NA | NA | Yes | Yes
VLP - Jetson | Rubalaxmi A | Export Elevation features ¦Regression Testing¦ Adhoc validation ¦Translation Testing ¦Test case Review | 0 | 0 | 0 | 0 | 0 | Selenium, cucumber framework | No | Yes | Yes | No | 0 | Yes | NA | Yes | Yes | GuruMoorthi Kumar Krishnan | CAT02621-01-02-01-1000 | Rahul More
VLP - Skyliner | Harish Kumar | Copy Assets¦File upload¦Conflict Validation¦View mission and Operator SummaryRegression | 0 | 0 | 0 | 0 | 0 | Playwright, Typescript | NA | Yes | Yes
VLP - Sprinters | Rahul More | Incident Playback ¦ Site Playback | 0 | 0 | 0 | 1 | 0 | Playwright, Python, Behave BDD | NA | Yes | Yes | NA | 2 | Yes | NA | Yes | Yes | Ram Gurusamy | CAT02621-01-02-01-1000 | Rahul More
VLP - Magicians | Balaji KP | [7 empty] | NA | Yes | NA | NA | NA | NA | NA | Yes | Yes
Warranty | Jerom Maria Selvam
CAT- Horizon App | Suhail A Mohammed | Enhancement testing ¦ Automation script creation | NA | 0 | 0 | 1 | NA | Playwright, Pytest, Request library, Python | NA | Yes | Yes | No | 5 | Yes | NA | Yes | NA
Remote Asset Monitoring - VisionLink | Dilleswara Rao, Lakhinana | Regression Fix ¦ CD Pipline Creation ¦ Notification Initial and Final Validation | NA | NA | NA | NA | NA | Karate | Maven | Yes | Yes | NO | NA | Yes | NA | yes | yes | Indumathi​ | CATX0552-01-01-01-1000 | Priyo
CAT - SIS2Go | Ramesh, Renugadevi | Functional Testing | 0 | 0 | 0 | NA | NA | Appium,Java,API | Maven | No | No | No | NA | NA | NA | Yes | Yes | Rajesh Ramesh | CAT02651-01-02-01-1000 | Renugadevi
CAT -MyUsed | Santhosh D | KT Sessions ¦Project Setup | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | yes | yes | Vijayagopan K.S | CAT02884-01-01-01-1000 | Renugadevi
DSP-Galaxy | Sangeetha | API Automation | NA | NA | NA | NA | NA | Karate ¦ Playwright | Maven ¦ NPM | Yes | Yes | No | No | Yes | NA | Yes | Yes | Indumathi​ | CAT02910-01-01-01-1000 | Salman

## RAG Config
RAG Configuration - Custom Thresholds Per Team
Engagement / Team | Story Points Assigned (higher) |  | Story Points Completed (higher) |  | US/Tasks pushed to next Sprint (lower) |  | Defect Leakage (%) (lower) |  | Production Incidents (#) (lower) |  | Open Risks & Issues (#) (lower) |  | Escalations (#) (lower) |  | Automation Coverage (%) (higher) |  | Automation Stability (%) (higher) |  | No of Auto Tool Proficiencies Req (higher) |  | No of Build Tool Proficiencies Req (higher)
| Expected | Variance | Expected | Variance | Expected | Variance | Expected | Variance | Expected | Variance | Expected | Variance | Expected | Variance | Expected | Variance | Expected | Variance | Expected | Variance | Expected | Variance
Default | [19 empty] | 1 |  | 1
CAT - Advanced Calculator | 24 | 2 | 24 | 2 | [15 empty] | 1 |  | 1
CAT Parts pricing | [19 empty] | 1 |  | 1
CAT- Technician Toolbox (TTB) | 24 | 2 | 24 | 2 | [15 empty] | 1 |  | 1
CAT-MCUI | 8 | 2 | 8 | 5 | [15 empty] | 1 |  | 1
CAT-MineStar Modularization | [19 empty] | 1 |  | 1
Common Services Program - Extension | 8 | 2 | 8 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2 | 1 | 1 | 1
Dealer Service Portal | 40 | 2 | 40 | 2 | [15 empty] | 1 |  | 1
DSP – BAAS/VLP/Customer Admin Tool | [19 empty] | 1 |  | 1
Dealer Service Portal - Billing | 32 | 2 | 32 | 2 | [15 empty] | 1 |  | 1
Dealer Service Portal - CIS | [19 empty] | 1 |  | 1
Dealer Service Portal - Gambit | 16 | 2 | 16 | 2 | 0 | 1 | 5 | 5 | 0 | 2 | 2 | 2 | 0 | 2 | 75 | 20 | 95 | 10 | 2 | 1 | 2 | 1
Foresight
Leadership Table 2
PCC - eCommerce - UI | 8 | 2 | 8 | 2
PSCS-Backend | 36 | 2 | 36 | 2
PSCS-Performance
VLP - Invaders
VLP - Jetson | 25 | 2 | 25 | 2
VLP - Skyliner | 21 | 2 | 21 | 2
VLP - Sprinters | 8 | 2 | 8 | 2
VLP - Magicians
Warranty | 9 | 2 | 9 | 2
CAT- Horizon App | 8 | 2 | 8 | 2
Remote Asset Monitoring - VisionLink | 8 | 2 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | 100 | 0 | 95 | 25 | 1 |  | 1
CAT - SIS2Go | 24 | 2 | 24 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA
CAT -MyUsed | 0 | 0 | 0 | 0
DSP-Galaxy | 24 | 2 | 24 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2 |  | 1

## Metrics Glossary
Metric Name | Category | Description | Expected Target (Green)
Story Points Assigned | Delivery | Number of story points assigned in the sprint | >= 8
Story Points Completed | Delivery | Number of story points completed in the sprint | >= 8
US/Tasks pushed to next Sprint | Delivery | User stories pushed to next sprint | 0
US/Tasks Assigned | Delivery | Number of user stories/tasks assigned | Informational
US/Tasks Completed | Delivery | Number of user stories/tasks completed | Informational
Defect Leakage (%) | Client Health | Percentage of defects leaked to production | <= 5
Production Incidents (#) | Client Health | Number of production incidents | 0
Open Risks & Issues (#) | Client Health | Open risks and issues | <= 2
Escalations (#) | Client Health | Number of escalations | 0
SOW Milestones | Client Health | Tracking of Statement of Work milestones | Informational
Automation Tool Proficiencies Required | Capability | Target proficiency or gaps for automation tools | <= 0 (Gap)
Build Tool Proficiencies Required | Capability | Target proficiency or gaps for build tools | <= 0 (Gap)
Cloud & DevOps Proficiencies (Azure/AWS) | Capability | Proficiency in Cloud and DevOps | Yes
CI/CD Pipeline Setup Proficiency | Capability | CI/CD setup capability | Yes
KT Documentation Prepared | Capability | Knowledge Transfer documentation completion | Yes
Automation Coverage (%) | Automation | Test automation coverage percentage | >= 75
Automation Stability (%) | Automation | Automation stability percentage | >= 95
Knowledge Transfer (#) | Automation | Knowledge transfer sessions conducted | Informational
Reusable Assets (#) | Automation | Reusable assets created/used | Informational
Regression Run Time (hrs) | Automation | Time taken to run regression suite with automation | Informational
Reg. Exec Time Without Auto (hrs) | Automation | Manual execution time of regression suite | Informational
Automation Bugs Reported | Automation | Bugs found by automation suite | Informational
CI/CD Maturity | Automation | CI/CD pipeline maturity flag | Yes
Deloitte Timesheet Filled | Compliance | Timely completion of Deloitte timesheet | Yes
Tenrox Timesheet Filled | Compliance | Timely completion of Tenrox timesheet | Yes
Process Compliance (%) | Compliance | Process compliance adherence based on timesheets | 100